## W & G
JIGAWA STATE SMALL TOWNS WATER SUPLLY AND SANITATION AGENCY (STOWA)
ANNUAL PROCUREMENT PLAN
PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS
| MINISTRY/ AGENCY: | STOWA
| BUDGET YEAR: | 2025
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Revised Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | Pre-Qualification | Bid Invitation | Bid receipt and opening | Bid Evaluation& Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | i. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2025/CP/REHAB./1 | NA | 800million | 350 million | open competitive method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 27/01/2025-10/03/2025 | 27/01/2025-10/03/2025 | 10/03/2025-17/03/2025 | 17/03/2025-21/03/2025 | 21/03/2025-28/03/2025 | 28/3/2025-03/04/2025 | 03/04/2025-04/04/2025 | 04/04/2025-02/05/2025 | 02/05/2024-09/05/2025 | First Quarter
Date: Actual
Cost :Plan | [11 empty] | 600000 |  | 60000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | ii. Procurement of materials in bulk under SMEs program | 020408/02 | STOWA/2025/CP/2 | NA | 100 million | 100 million | sellective method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost :Plan | [13 empty] | 40000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | iii.Conversion and upgrading of 50No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2025/PROJ/CP/3 | NA | 750 Million | 375 Million | Open competitive Method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 27/01/2025-10/03/2025 | 27/01/2025-10/03/2025 | 10/03/2025-17/03/2025 | 17/03/2025-21/03/2025 | 21/03/2025-28/03/2025 | 28/3/2025-03/04/2025 | 03/04/2025-04/04/2025 | 04/04/2025-02/05/2025 | 02/05/2024-09/05/2025 | first Quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | iv. Reinforcement/improvement of reticulation for 20km in 20No. Small towns | 020406/02 | STOWA/2025/CP/4 | NA | 50million | 20million | Selective competitive Method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | v. Cmmencement of 2025 constituency projects | 020408/02 | STOWA/2025/CP/5 | NA | 193.0million | 193.0million | Selective competitive Method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | 50000 |  |  | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | vi. Completion of 2023/2024 constituency project | 020408/02 | STOWA/2025/CP/6 | NA | 200 million | 100 million | Ongoing project | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project | [5 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | vii. Establishhment of WCA in community and several follow up visit to 200 communities for monitoring of activities | 020411/02 | STOWA/2025/WCA/7 | NA | 10million | 10million | Direct method | 19/01/2025-16/01/2025 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 21/02/2025-28/02/2025 | Direct | Direct | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 60000 |  |  | 80000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | vii. Procurement of 1No. Toyota Hillux | 020411/02 | STOWA/2025/8 | NA | 80million | 80million | Sellective method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 60000 |  |  | 80000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | ix Capacity building of Technical personals on solar based installation and maintenance | 020411/02 | STOWA/2025/CP/9 | NA | 5million | 5 million | Direct method | 19/01/2025-16/01/2025 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 21/02/2025-28/02/2025 | Direct | Direct | 28/03/2025-04/4/2025 | second -quarter
Date: Actual
Cost: Plan | [10 empty] | 50000 | [7 empty] | 20000
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | x. Construction of 2No. Public convenience at small towns | 020412/02 | STOWA/2025/CP/10 | NA | 10 million | 10 millioin | Nominative Method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First quarter
Date: Actual
Cost :Plan | [7 empty] | 50000 |  |  | 40000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xi. Drlling of 20No. additional complete boreholes accessories | 020406/02 | STOWA/2025/CP/11 | NA | 41.42million | 16.56million | Nominative Method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xii. Construction of 14No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2025/CP/12 | NA | 300 million | 107.15 million | sellective method | 19/01/2025-16/01/2025 | 17/01/2025-24/01/2025 | NA | NA | 24/01/2025-31/01/2025 | 24/01/2025-31/01/2025 | 31/01/2025-07/02/2025 | 07/02/2025-14/02/2025 | 14/02/2025-21/02/2025 | 21/02/2025-28/02/2025 | 28/02/2025-07/3/2025 | 07/3/2025-28/03/2025 | 28/03/2025-04/4/2025 | First quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiii.Conversion and upgrading of 50No. motorized water supply schemes to solar powered water supply schemes | 020408/02 | STOWA/2025/CP/13 | NA | 750 Million | 300 Million | Open competitive Method | 9/4/2025-16/4/2025 | 16/4/2025-30/4/2025 | NA | NA | 30/4/2025-11/6/2025 | 30/4/2025-11/6/2025 | 11/6/2025-18/6/2025 | 18/6/2025-20/6/2025 | 20/6/2025-27/6/2025 | 27/6/2025-4/7/2025 | 04/07/2025-11/7/2025 | 11/7/2025-15/8/2025 | 15/8/2025-22/8/2025 | second quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xiv. Completion of 2023/2024 constituency project | 020408/02 | STOWA/2025/CP/14 | NA | 200 million | 70 million | Ongoing project | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 11/7/2025-15/8/2025 | 15/8/2025-22/8/2025 | second -quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xv. Construction of 14No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2025/CP/15 | NA | 300million | 107.5million | selective competitive Method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 150000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvi. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2025/CP/16 | NA | 800million | 300 million | Open Competitive method | 9/4/2025-16/4/2025 | 16/4/2025-30/4/2025 | NA | NA | 30/4/2025-11/6/2025 | 30/4/2025-11/6/2025 | 11/6/2025-18/6/2025 | 18/6/2025-20/6/2025 | 20/6/2025-27/6/2025 | 27/6/2025-4/7/2025 | 04/07/2025-11/7/2025 | 11/7/2025-15/8/2025 | 15/8/2025-22/8/2025 | second -quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvii.Procurement of materials in bulk under SMEs program | 020404/02 | STOWA/2025/CP/17 | NA | 100 Million | 100 Million | selective competitive Method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xviii. Commencement of construction of water supply facilities under 2025 constituency project | 020408/02 | STOWA/2025/CP/18 | NA | 193 million | 193 million | sellective method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [7 empty] | 20000 |  |  | 30000 |  |  | 120000 | 30000 |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xix. Construction of 2No.public convenience at small towns | 020412/02 | STOWA/2025/CP/19 | NA | 10 million | 10million | Nominative Method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 |  |  | 50000 | [7 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xx. Reinforcement/improvement of reticulation for 20km in 20No. Small towns | 020406/02 | STOWA/2025/CP/20 | NA | 50million | 20 million | Selective method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxi. Drilling of 20km additional complete boreholes with accessories | 020406/02 | STOWA/2025/CP/21 | NA | 41.42million | 16.58million | Nominative Method | 9/4/2025-16/4/2025 | 16/4/2025-23/4/2025 | NA | NA | 23/4/2025-7/5/2025 | 23/4/2025-7/5/2025 | 07/05/2025-14/5/2025 | 14/05/2025-16/05/2025 | 16/05/2025-23/05/2025 | 23/05/2025-30/05/20225 | 30/05/2025-04/06/2025 | 04/06/2025-8/08/2025 | 8/08/2025-15/08/2025 | second -quarter
Date: Actual
Cost :Plan | [18 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxii. Rehabilitation of existing small towns water supply schemes | 020404/02 | STOWA/2025/CP/22 | NA | 800million | 150 million | Selective Competitive method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiii.Procurement of materials in bulk under SMEs program | 020404/02 | STOWA/2025/CP/23 | NA | 100 Million | 100 Million | selective competitive Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxiv.Conversion and upgrading of 50No. motorized water supply scheme to solar powered water supply schemes | 020408/02 | STOWA/2023/PROJ/CP/24 | NA | 750 Million | 75 Million | selective competitive Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxv. Construction of 14No. New conventional solar water schemes across the 7 zones | 020408/02 | STOWA/2025/CP/25 | NA | 300million | 85million | selective competitive Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [18 empty] | 150000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxvi. Completion for the construction of water supply facilities under 2023/2024 constituency project | 020408/02 | STOWA/2025/CP/26 | NA | 200 million | 30 million | Ongoing project | Ongoing project | ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | Ongoing project | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost: Plan | [7 empty] | Ongoing project |  |  | ongoing project |  | ongoing project
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xvii. Commencement of construction of water supply facilities under 2025 constituency project | 020408/02 | STOWA/2025/CP/27 | NA | 193 million | 193 million | sellective method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [10 empty] | 30000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxviii Capacity building of Technical personals on solar based installation and maintenance | 020411/02 | STOWA/2025/CP/28 | NA | 5million | 5 million | Direct method | 17/07/2025-24/07/2025 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 29/08/2025-04/09/2025 | Direct | Direct | 25/09/2025-30/09/2025 | Third -quarter
Date: Actual
Cost: Plan
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxix. Procurement of 1No. Toyota Hillux | 020411/02 | STOWA/2025/CP/29 | NA | 80million | 80million | Sellective method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxx.Establishment of WCAs in communities and several follow up visit to 200 communities for monitoring of activities | 020411/02 | STOWA/2025/WCA/30 | NA | 10million | 10million | Direct | 17/07/2025-24/07/2025 |  | NA | Direct | Direct | Direct | Direct | Direct | Direct | 29/08/2025-04/09/2025 | Direct | Direct | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxi. Construction of 2No. Public convenience at small towns | 020412/02 | STOWA/2025/CP/31 | NA | 10 million | 10 millioin | Nominative Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxii. Reinforcement/improvement of reticulation for 20km in 20No. Small towns | 020406/02 | STOWA/2025/CP/32 | NA | 50million | 10 million | Nominative Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [18 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxiii. Drilling of 20km additional complete boreholes with accessories | 020406/02 | STOWA/2025/CP/33 | NA | 41.42million | 8.26million | Nominative Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [18 empty] | 30000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxiv. Capacity building of Technical Personnel on solar based installation and maintenance | 020411/02 | STOWA/2022/SEMINAR/34 | NA | 5million | 5million | Direct | 6/10/2025-20/10/2025 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 29/08/2025-04/09/2025 | Direct | Direct | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | [6 empty] | MD |  | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxvi.Procurement of materials in bulk under SMEs program | 020404/02 | STOWA/2025/CP/35 | NA | 100 Million | 100 Million | selective competitive Method | 17/07/2025-24/07/2025 | 24/07/2025-31/07/2025 | NA | NA | 31/07/2025-14/08/2025 | 31/07/2025-14/08/2025 | 14/08/2025-21/08/2025 | 21/08/2025-22/08/2025 | 22/08/2025-29/08/2025 | 29/08/2025-04/09/2025 | 04/09/2025-25/09/2025 | 25/09/2025-30/09/2025 | 30/09/2025-07/10/2025 | Third -quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxvii. Construction of 2No. Public convenience at small towns | 020412/02 | STOWA/2025/CP/36 | NA | 10 million | 10 millioin | Nominative Method | 11/10/2025-18/07/2025 | 18/10/2025-25/10/2025 | NA | NA | 25/10/2025-09/11/2025 | 25/10/2025-09/11/2025 | 09/11/2025-14/11/2025 | 14/11/2025-16/11/2025 | 16/11/2025-23/11/2025 | 23/11/2025-30/11/2025 | 30/11/2025-1/12/2025 | 1/12/2025-22/12/2025 | 22/12/2025-29/12/2025 | Fourth Quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxviii Capacity building of Technical personals on solar based installation and maintenance | 020411/02 | STOWA/2025/SEMINAR/37 | NA | 5million | 5 million | Direct method | 11/10/2025-18/07/2025 | Direct | NA | Direct | Direct | Direct | Direct | Direct | Direct | 23/11/2025-30/11/2025 | Direct | Direct | 1/12/2025-22/12/2025 | Fourth Quarter
Date: Actual
Cost: Plan
Cost : Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxix.Establishment of WCAs in communities and several follow up visit to 200 communities for monitoring of activities | 020411/02 | STOWA/2025/WCA/38 | NA | 10million | 10million | Direct | 11/10/2025-18/07/2025 |  | NA | Direct | Direct | Direct | Direct | Direct | Direct | 23/11/2025-30/11/2025 | Direct | Direct | 1/12/2025-22/12/2025 | Fourth -quarter
Date: Actual
Cost :Plan
Cost: Actual
Responsibility | [7 empty] | Director Community Mobilization | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxx. Commencement of construction of water supply facilities under 2025 constituency project | 020408/02 | STOWA/2025/CP/39 | NA | 193 million | 193 million | sellective method | 11/10/2025-18/07/2025 | 18/10/2025-25/10/2025 | NA | NA | 25/10/2025-09/11/2025 | 25/10/2025-09/11/2025 | 09/11/2025-14/11/2025 | 14/11/2025-16/11/2025 | 16/11/2025-23/11/2025 | 23/11/2025-30/11/2025 | 30/11/2025-1/12/2025 | 1/12/2025-22/12/2025 | 22/12/2025-29/12/2025 | Fourth -quarter
Date: Actual
Cost :Plan | [10 empty] | 30000 | [7 empty] | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G. Due Procrss | Executive Governor | MD | Director Technical Support | Commissioner of Finance
Date: Plan | xxxxi.Procurement of materials in bulk under SMEs program | 020404/02 | STOWA/2025/CP/40 | NA | 100 Million | 100 Million | selective competitive Method | 11/10/2025-18/07/2025 | 18/10/2025-25/10/2025 | NA | NA | 25/10/2025-09/11/2025 | 25/10/2025-09/11/2025 | 09/11/2025-14/11/2025 | 14/11/2025-16/11/2025 | 16/11/2025-23/11/2025 | 23/11/2025-30/11/2025 | 30/11/2025-1/12/2025 | 1/12/2025-22/12/2025 | 22/12/2025-29/12/2025 | Fourth -quarter
Date: Actual
Cost :Plan | [7 empty] | 70000 |  |  | 50000 |  |  | 120000 |  |  |  |  | 50000
Cost: Actual
Responsibility | [7 empty] | Procurement Officer | D.G Due Process |  | Procurement Officer | Procurement Officer | Procurement Officer | Procurement Officer | MD | D.G Due Process | Executive Governor | MD | Director Technical Support | Commissioner of Finance

## CS
PROCUREMENT PLAN FOR CONSULTING SERVICES.
MINISTRY/ AGENCY:
BUDGET YEAR:
Project Description | Package Number | CONTRACT TYPE |  |  |  | PREPARATION OF PROPOSALS |  |  |  | SHORTLIST |  | CONSULTANT PROPOSAL |  | PROPOSAL EVALUATION AND NEGOTIATION | [5 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
|  | Lumpsum or Time-Based | Budgetary Amount in Naira | Plan Vs Actual | Approval Threshhold | Preparation and Submission by MDAs | MDA Approval/ LASPPA 'Certificate of Compliance" | Advertisement | Lead-Time Beforte Shortlist | Submission Date | MDA Approval/ LASPPA 'Certificate of Compliance" | Invitation Date | Submission / Opening Date | Submission Evaluation Report (T) | MDA Approval/ LASPPA 'Certificate of Compliance" | Opening/ Evaluation of Financial Proposals | Submission Evaluation Report (T) (F) | Negotiation (if any) | Certificate of Clearance Date | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion