## W & G
JIGAWA STATE DUE PROCESS AND PROJECT MONITORING BUREAU
PROCUREMENT PLAN TEMPLATE
PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS
| MINISTRY/ AGENCY: | LBRARY BOARD
| BUDGET YEAR: | 2025
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Approved Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | prequalification | Bid Invitation | Bid receipt and opening | Bid Evaluation& Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | Renovation of Jahun Divisional Library | 051700800100 060033 |  |  | 38'000'000 | 13,000,000=00 | Nominative | 06-01-2025 13-01-2025 | 15-01-2025 17-01-2025 | 17-01-2025 21-01-2025 | 21-01-2025 24-01-2025 | 24-01-2025 29-01-2025 | 31-01-2025 05-02-2025 | 13-02-2025 13-02-2025 | 13-02-2025 20-02-2025 | 20-02-2025 22-02-2025 | 22-02-2025 24-02-2025 | 24-02-2025 28-02-2025 | 28-02-2025 28-03-2025 | 28-03-2025 12-04-2025 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Cost: Actual
Responsibility | [7 empty] | Director Planing | DG. Due Process | Planing Com. | Planing Com. | Planing Com. | Planing Com. | Tech. Comm. | Tech. Comm. | DG. Due Process | Council Afairs | Executive Secretary | E.S. / Director Planing | Finance Connisionor
Date: Plan | Prcurement of Library Materials | 051700800100 060033 |  |  | 38,000;000 | 6,000;000 | Nominative | 08-01-2025 15-01-2025 | 15-01-2025 22-01-2025 | 22-01-2025 24-01-2025 | 24-01-2025 28-01-2025 | 28-01-2025 30-01-2025 | 30-01-2025 05-02-2025 | 30-01-2025 05-02-2025 | 05-02-2025 10-02-2025 | 17-02-2025 24-02-2025 | 25-02-2025 26-02-2025 | 26-02-2025 28-02-2025 | 28-02-2025 20-03-2025 | 20-03-2025 30-03-2025 | First Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Cost: Actual | [7 empty] | 25000
Responsibility | [7 empty] | Director Planing | DG. Due Process | Planing Com. | Planing Com. | Planing Com. | Planing Com. | Tech. Comm. | Tech. Comm. | DG. Due Process | Council Afairs | Executive Secretary | E.S. / Director Planing | Finance Connisionor
Date: Plan | Procurement of ICT Materials | 051700800100 060033 |  |  | 38,000;000 | 6,000,000=00 | Nominative | 01-04-2025 08-04-2025 | 08-04-2025 10-04-2025 | 10-04-2025 15-04-2025 | 15-04-2025 18-04-2025 | 18-04-2025 22-04-2025 | 22-04-2025 25-04-2025 | 25-04-2025 30-04-2025 | 30-04-2025 02-05-2025 | 02-05-2025 09-05-2025 | 09-05-2025 14-05-2025 | 14-05-2025 16-05-2025 | 16-05-2025 26-06-2025 | 26-06-2025 10-07-2025 | Second Quarter
Date: Actual | [9 empty] | _ | _ | _ | _ | _ | [6 empty] | Second Quarter
Cost :Plan | [7 empty] | 20000 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Cost: Actual | [7 empty] | 17000
Responsibility | [7 empty] | Director Planing | DG. Due Process | Planing Com. | Planing Com. | Planing Com. | Planing Com. | Tech. Comm. | Tech. Comm. | DG. Due Process | Council Afairs | Executive Secretary | E.S. / Director Planing | Finance Connisionor
Date: Plan | Bulk Purchase of Library Books | 051700800100 060033 |  |  | 38,000;000 | 5,000;000 | Nomnative | 02-04-2025 09-04-2025 | 09-04-2025 05-04-2025 | 15-04-2025 18-04-2025 | 18-04-2025 23-04-2025 | 23-04-2025 25-04-2025 | 25-04-2025 29-04-2025 | 29-04-2025 01-05-2025 | 01-05-2025 06-05-2025 | 06-05-2025 13-05-2025 | 13-05-2025 16-05-2025 | 16-05-2025 20-05-2025 | 20-05-2025 12-06-2025 | 12-06-2025 30-06-2025
Date: Actual | [20 empty] | Second Quarter
Cost :Plan | [7 empty] | 25000 | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
Cost: Actual | [7 empty] | 20000
Responsibility | [7 empty] | Director Planing | DG. Due Process | Planing Com. | Planing Com. | Planing Com. | Planing Com. | Tech. Comm. | Tech. Comm. | DG. Due Process | Council Afairs | E/S | E.S. / Director Planing | Finance Connisionor
Date: Plan | Construction of Six Seater Toilet at the State Main Library | 051700800100 060033 |  |  | 38,000;000 | 8000000 | Nomnative | 02-07-2025 09-07-2025 | 09-07-2025 16-07-2025 | 16-07-2025 18-07-2025 | 18-07-2025 22-07-2025 | 22-07-2025 24-07-2025 | 24-07-2025 28-07-2025 | 28-07-2025 30-07-2025 | 30-07-2025 05-08-2025 | 05-08-2025 08-08-2025 | 08-08-2025 11-08-2025 | 11-08-2025 16-08-2025 | 16-08-2025 20-09-2025 | 20-09-2025 30-09-2025 | Third Quarter
Date: Actual
Cost :Plan | [7 empty] | 30000
Cost: Actual
Responsibility
Date: Plan | [7 empty] | Director Planing | DG. Due Process | Planing Com. | Planing Com. | Planing Com. | Planing Com. | Tech. Comm. | Tech. Comm. | DG. Due Process | Council Afairs | E/S | E.S. / Director Planing | Finance Connisionor
Date: Actual
Cost :Plan | [8 empty] | _
Cost: Actual
Responsibility
Date: Plan
Date: Actual
Cost :Plan | [8 empty] | _
Cost: Actual
Responsibility
[9 empty] | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _
[9 empty] | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _ | _

## CS
PROCUREMENT PLAN FOR CONSULTING SERVICES.
MINISTRY/ AGENCY:
BUDGET YEAR:
Project Description | Package Number | CONTRACT TYPE |  |  |  | PREPARATION OF PROPOSALS |  |  |  | SHORTLIST |  | CONSULTANT PROPOSAL |  | PROPOSAL EVALUATION AND NEGOTIATION | [5 empty] | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
|  | Lumpsum or Time-Based | Budgetary Amount in Naira | Plan Vs Actual | Approval Threshhold | Preparation and Submission by MDAs | MDA Approval/ LASPPA 'Certificate of Compliance" | Advertisement | Lead-Time Beforte Shortlist | Submission Date | MDA Approval/ LASPPA 'Certificate of Compliance" | Invitation Date | Submission / Opening Date | Submission Evaluation Report (T) | MDA Approval/ LASPPA 'Certificate of Compliance" | Opening/ Evaluation of Financial Proposals | Submission Evaluation Report (T) (F) | Negotiation (if any) | Certificate of Clearance Date | Contract Amount in Naira | Contract Offer | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost | Action Party | Champion